## Module Timeline
Module Timeline
Start and end per module, rolled up from the Dev Task List. Gantt bars are by week (week starting Monday).
Module ID | Module | Track | Starts after | Planned start | Planned end | Working days | Features | Screens | Done | % done | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10
M00 | Global / Shell | Track A | Project start | 2026-10-19 | 2026-10-29 | 9 | 5 | 0 | 0 | 0% | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M02 | Appointments | Track A | M00 Global / Shell | 2026-10-30 | 2026-12-29 | 38 | 20 | 26 | 0 | 0% | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M03 | Patients | Track B | M00 Global / Shell | 2026-10-30 | 2027-03-11 | 86 | 40 | 45 | 0 | 0% | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M05 | Account | Track C | M00 Global / Shell | 2026-10-30 | 2026-11-17 | 12 | 11 | 11 | 0 | 0% | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M01 | Dashboard | Track A | M02 Appointments | 2027-01-04 | 2027-01-14 | 9 | 6 | 1 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M04 | Reports | Track C | M05 Account | 2026-11-18 | 2026-12-04 | 12 | 6 | 6 | 0 | 0% | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Whole project |  |  | 2026-10-19 | 2027-03-11 | 95 | 88 | 89 | 0 | 0% | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned start of a module can be overridden by typing a date over it; its tasks and later modules shift automatically.

## Dev Task List
Oralux Dentist Portal — Dev Task List
One row per feature. Screens and Figma links come from https://www.figma.com/design/dAKa9xPhXAuRKat5jGS8Hx/Dentist. Dates come from Setup and Module Timeline.
Task ID | Module ID | Module | Sub-module | Feature / Task | Description | Screens | Screen names (Figma frames) | Figma | Est. days | Planned start | Planned end | Assignee | Status | Actual start | Actual end | Remarks
M00.01.01 | M00 | Global / Shell | Navigation & Layout | Org / clinic switcher | Clinic logo and name with 'Powered by oralux'; collapse-panel toggle. | 0 | Shared UI — appears on other screens |  | 1 | 2026-10-19 | 2026-10-19 |  | Not started
M00.01.02 | M00 | Global / Shell | Navigation & Layout | Sidebar menu | Links to Dashboard, Appointments (Schedule), Patients and Reports. | 0 | Shared UI — appears on other screens |  | 2 | 2026-10-20 | 2026-10-21 |  | Not started
M00.01.03 | M00 | Global / Shell | Navigation & Layout | Global search (⌘K) | Search patients and records from anywhere. | 0 | Shared UI — appears on other screens |  | 3 | 2026-10-22 | 2026-10-26 |  | Not started
M00.01.04 | M00 | Global / Shell | Navigation & Layout | Notifications | Bell with unread count badge. | 0 | Shared UI — appears on other screens |  | 2 | 2026-10-27 | 2026-10-28 |  | Not started
M00.01.05 | M00 | Global / Shell | Navigation & Layout | User menu | Logged-in dentist name, email and avatar; entry to Account. | 0 | Shared UI — appears on other screens |  | 1 | 2026-10-29 | 2026-10-29 |  | Not started
M01.01.01 | M01 | Dashboard | Overview | Greeting & day summary | Greeting, date and number of appointments today. | 1 | Dashboard — Dentist · Overview | Open | 1 | 2027-01-04 | 2027-01-04 |  | Not started
M01.01.02 | M01 | Dashboard | Overview | Today's schedule | Timeline of today's appointments with status; next free slot; View all. | 0 | Shared UI — appears on other screens |  | 2 | 2027-01-05 | 2027-01-06 |  | Not started
M01.01.03 | M01 | Dashboard | Overview | Up next card | Next patient in N minutes with procedure/tooth; View patient / Dental chart shortcuts. | 0 | Shared UI — appears on other screens |  | 1 | 2027-01-07 | 2027-01-07 |  | Not started
M01.01.04 | M01 | Dashboard | Overview | Appointment requests widget | Pending requests with Accept / Decline. | 0 | Shared UI — appears on other screens |  | 2 | 2027-01-08 | 2027-01-11 |  | Not started
M01.01.05 | M01 | Dashboard | Overview | Patients seen per month | Bar chart of the last 6 months with % change. | 0 | Shared UI — appears on other screens |  | 2 | 2027-01-12 | 2027-01-13 |  | Not started
M01.01.06 | M01 | Dashboard | Overview | Recent patients | Patients from the most recent visits. | 0 | Shared UI — appears on other screens |  | 1 | 2027-01-14 | 2027-01-14 |  | Not started
M02.01.01 | M02 | Appointments | Calendar Views | Day view | Hourly timeline per dentist with status counts, Next up, and the requests panel. | 2 | Appointments - Day Appointments - Day | Open | 4 | 2026-10-30 | 2026-11-05 |  | Not started
M02.01.02 | M02 | Appointments | Calendar Views | Date filter | Date picker to jump to a specific day. | 1 | Appointments - Day · Date filter | Open | 1 | 2026-11-06 | 2026-11-06 |  | Not started
M02.01.03 | M02 | Appointments | Calendar Views | Week view | Week grid with appointment counts per day. | 1 | Appointments - Week | Open | 3 | 2026-11-09 | 2026-11-11 |  | Not started
M02.01.04 | M02 | Appointments | Calendar Views | Month view | Month grid of appointments. | 1 | Appointments - Month | Open | 3 | 2026-11-12 | 2026-11-16 |  | Not started
M02.01.05 | M02 | Appointments | Calendar Views | Filters & toolbar | Today, treatment filter, chair filter, Day/Week/Month toggle, Full screen, New appointment. | 0 | Shared UI — appears on other screens |  | 2 | 2026-11-17 | 2026-11-18 |  | Not started
M02.01.06 | M02 | Appointments | Calendar Views | Status legend & summary | Confirmed, Pending, Rescheduled, Cancelled, Completed, In chair, Checked in, No-show. | 0 | Shared UI — appears on other screens |  | 1 | 2026-11-19 | 2026-11-19 |  | Not started
M02.02.01 | M02 | Appointments | Appointment Details | View details | Appointment details modal opened from the calendar. | 1 | Appointments - Day · Details · Modal | Open | 2 | 2026-11-20 | 2026-11-23 |  | Not started
M02.02.02 | M02 | Appointments | Appointment Details | Status states | Details modal for Pending, Confirmed, Rescheduled, Cancelled and Completed. | 6 | Details modal · Pending Details modal · Confirmed Details modal · Rescheduled Details modal · Cancelled Details modal · Completed Details modal · Completed | Open | 3 | 2026-11-24 | 2026-11-26 |  | Not started
M02.02.03 | M02 | Appointments | Appointment Details | Reschedule | Pick a new date and time for an appointment. | 1 | Details modal · Reschedule | Open | 2 | 2026-11-27 | 2026-12-01 |  | Not started
M02.02.04 | M02 | Appointments | Appointment Details | Cancel appointment | Confirmation dialog for cancelling. | 1 | Cancel dialog | Open | 1 | 2026-12-02 | 2026-12-02 |  | Not started
M02.02.05 | M02 | Appointments | Appointment Details | More actions menu | Overflow actions on a confirmed appointment. | 1 | Details modal · Confirmed · More action open | Open | 1 | 2026-12-03 | 2026-12-03 |  | Not started
M02.02.06 | M02 | Appointments | Appointment Details | Change procedure | Multi-select to change the booked procedures. | 1 | Details modal · Change procedure · Multi-select | Open | 2 | 2026-12-04 | 2026-12-07 |  | Not started
M02.02.07 | M02 | Appointments | Appointment Details | Last visit history | Expandable summary of the patient's last visit. | 1 | Details modal · Last visit (expanded) | Open | 1 | 2026-12-09 | 2026-12-09 |  | Not started
M02.03.01 | M02 | Appointments | Add Appointment | Select patient | Search and pick a patient (empty, dropdown and selected states). | 3 | Appointments - Add appointment · Select patient (1 empty) Appointments - Add appointment · Select patient (2 dropdown) Appointments - Add appointment · Select patient (3 selected) | Open | 2 | 2026-12-10 | 2026-12-11 |  | Not started
M02.03.02 | M02 | Appointments | Add Appointment | Select procedure & schedule | Choose procedures, dentist, date and time. | 1 | Appointments - Add appointment | Open | 3 | 2026-12-14 | 2026-12-16 |  | Not started
M02.03.03 | M02 | Appointments | Add Appointment | All procedures list | Browse the full procedure catalogue. | 1 | Appointments - Add appointment · All procedures | Open | 1 | 2026-12-17 | 2026-12-17 |  | Not started
M02.03.04 | M02 | Appointments | Add Appointment | Review & confirm | Summary before booking. | 1 | Appointments - Add appointment · Review & confirm | Open | 1 | 2026-12-18 | 2026-12-18 |  | Not started
M02.03.05 | M02 | Appointments | Add Appointment | Booking confirmation | Success state after booking. | 1 | Appointments - Add appointment · Booked | Open | 1 | 2026-12-21 | 2026-12-21 |  | Not started
M02.04.01 | M02 | Appointments | Appointment Requests | Requests drawer | Search requests; Accept / Decline; New / Approved / Declined tabs. | 1 | Appointments — Calendar - Requests drawer | Open | 3 | 2026-12-22 | 2026-12-28 |  | Not started
M02.04.02 | M02 | Appointments | Appointment Requests | Request details | Full details of a single request. | 1 | Appointments — Calendar - Requests drawer · View details | Open | 1 | 2026-12-29 | 2026-12-29 |  | Not started
M03.01.01 | M03 | Patients | Patient List | Patient list | Table of name, dentist, last procedure, last visit, balance, status; search; pagination. | 1 | Patients — List | Open | 3 | 2026-10-30 | 2026-11-04 |  | Not started
M03.02.01 | M03 | Patients | Add Patient | Add patient form | Photo, patient information, contact details, tags and notes. | 1 | Patients — Add patient · Modal · v2 (field list) · Desktop | Open | 3 | 2026-11-05 | 2026-11-09 |  | Not started
M03.02.02 | M03 | Patients | Add Patient | Add success | Confirmation after the record is created. | 1 | Patients — Add patient · Success · Desktop | Open | 1 | 2026-11-10 | 2026-11-10 |  | Not started
M03.02.03 | M03 | Patients | Add Patient | Duplicate detection | Compare the new entry with a matching existing record (% match). | 1 | Patients — Add patient · Duplicate found · v1 (comparison) · Desktop | Open | 3 | 2026-11-11 | 2026-11-13 |  | Not started
M03.02.04 | M03 | Patients | Add Patient | Merge records | Confirm merging with the existing record. | 1 | Patients — Add patient · Merge confirmation · Desktop | Open | 2 | 2026-11-16 | 2026-11-17 |  | Not started
M03.02.05 | M03 | Patients | Add Patient | Merge success | Confirmation after merging. | 1 | Patients — Add patient · Merge success · Desktop | Open | 1 | 2026-11-18 | 2026-11-18 |  | Not started
M03.03.01 | M03 | Patients | Patient Details · Header | Patient summary | ID, name, status, member since, age, DOB, gender, primary dentist, last visit. | 0 | Shared UI — appears on other screens |  | 2 | 2026-11-19 | 2026-11-20 |  | Not started
M03.03.02 | M03 | Patients | Patient Details · Header | Quick actions | Message, Book appointment, Print information, Update, More action. | 0 | Shared UI — appears on other screens |  | 2 | 2026-11-23 | 2026-11-24 |  | Not started
M03.03.03 | M03 | Patients | Patient Details · Header | Outstanding balance | Balance and last payment; Add payment; View statement. | 0 | Shared UI — appears on other screens |  | 1 | 2026-11-25 | 2026-11-25 |  | Not started
M03.03.04 | M03 | Patients | Patient Details · Header | Recent activity | Audit feed of changes to the patient record. | 0 | Shared UI — appears on other screens |  | 2 | 2026-11-26 | 2026-11-27 |  | Not started
M03.04.01 | M03 | Patients | General | View general info | Contact, emergency contact, other info, data-privacy consent, insurance, membership, notes. | 1 | Patients — Details · General 1 · Desktop | Open | 2 | 2026-12-01 | 2026-12-02 |  | Not started
M03.04.02 | M03 | Patients | General | Edit general info | Edit mode for the General tab. | 1 | Patients — Details · General 1 · Edit · Desktop | Open | 2 | 2026-12-03 | 2026-12-04 |  | Not started
M03.05.01 | M03 | Patients | Medical History | View medical history | Answers to medical questions; last reviewed; Mark as reviewed. | 1 | Patients — Details · Medical History · Layout C · Desktop | Open | 2 | 2026-12-07 | 2026-12-09 |  | Not started
M03.05.02 | M03 | Patients | Medical History | Edit medical history | Edit mode for medical history answers. | 1 | Patients — Details · Medical History · Layout C · Edit · Desktop | Open | 3 | 2026-12-10 | 2026-12-14 |  | Not started
M03.06.01 | M03 | Patients | Dental Record Chart | Chart · collapsed | Chart with the findings summary collapsed. | 1 | Patients — Details · Dental Record Chart · Many findings · Collapsed · Desktop | Open | 5 | 2026-12-15 | 2026-12-21 |  | Not started
M03.06.02 | M03 | Patients | Dental Record Chart | Chart · expanded | Chart with the summary of conditions per tooth expanded. | 1 | Patients — Details · Dental Record Chart · Many findings · Expanded · Desktop | Open | 3 | 2026-12-22 | 2026-12-28 |  | Not started
M03.06.03 | M03 | Patients | Dental Record Chart | Full-screen chart | Distraction-free chart editing. | 1 | Patients — Dental Record Chart · Full screen · Desktop | Open | 3 | 2026-12-29 | 2027-01-05 |  | Not started
M03.07.01 | M03 | Patients | Transaction Record | Transaction list | Filter by All / Paid / Unpaid / Partial / Cancelled; date range; pagination. | 1 | Patients — Details · Transaction Record · Desktop | Open | 3 | 2027-01-06 | 2027-01-08 |  | Not started
M03.07.02 | M03 | Patients | Transaction Record | Add transaction · type | Choose the transaction type (Procedure, Purchase item). | 1 | Patients — Details · Transaction Record · Add transaction · Transaction type · Layout B · Desktop | Open | 1 | 2027-01-11 | 2027-01-11 |  | Not started
M03.07.03 | M03 | Patients | Transaction Record | Procedure transaction | New procedure form: line items with procedure, tooth no., cost, discount and total; search-as-you-type for procedures; Save transaction. | 2 | Patients — Details · Transaction Record · Add transaction · Procedure · Layout B · Desktop Patients — Details · Transaction Record · Add transaction · Procedure · Layout B · Typing a procedure · Desktop | Open | 3 | 2027-01-12 | 2027-01-14 |  | Not started
M03.07.04 | M03 | Patients | Transaction Record | Add procedure | Add a procedure line with tooth no., cost, discount and total cost. | 1 | Patients — Details · Transaction Record · Add transaction · Procedure · Add procedure · Desktop | Open | 2 | 2027-01-15 | 2027-01-18 |  | Not started
M03.07.05 | M03 | Patients | Transaction Record | Browse all procedures | Full procedure catalogue with prices to pick from. | 1 | Patients — Details · Transaction Record · Add transaction · Procedure · Add procedure · All procedures · Desktop | Open | 1 | 2027-01-19 | 2027-01-19 |  | Not started
M03.07.06 | M03 | Patients | Transaction Record | Purchase item transaction | New purchase form: items with quantity and unit price; Save transaction. | 1 | Patients — Details · Transaction Record · Add transaction · Purchase Item · Desktop | Open | 2 | 2027-01-20 | 2027-01-21 |  | Not started
M03.07.07 | M03 | Patients | Transaction Record | Add item | Add a purchase item line. | 1 | Patients — Details · Transaction Record · Add transaction · Purchase Item · Add item · Desktop | Open | 1 | 2027-01-22 | 2027-01-22 |  | Not started
M03.07.08 | M03 | Patients | Transaction Record | Browse all items | Item catalogue with stock and price to pick from. | 1 | Patients — Details · Transaction Record · Add transaction · Purchase Item · Add item · All items · Desktop | Open | 1 | 2027-01-25 | 2027-01-25 |  | Not started
M03.08.01 | M03 | Patients | Statement of Account | Statement of account | Date range ledger with amount, payments and running balance; Print. | 1 | Patients — Details · Statement of Account · Layout B · Desktop | Open | 3 | 2027-01-26 | 2027-01-28 |  | Not started
M03.09.01 | M03 | Patients | Docs | Document list | Table of documents with type filter. | 1 | Patients — Details · Docs · Layout C · Desktop | Open | 2 | 2027-01-29 | 2027-02-01 |  | Not started
M03.09.02 | M03 | Patients | Docs | Row actions menu | Per-document actions. | 1 | Patients — Details · Docs · Layout C · Row menu · Desktop | Open | 1 | 2027-02-02 | 2027-02-02 |  | Not started
M03.09.03 | M03 | Patients | Docs | Add document · choose type | Pick Prescription, Dental Certificate, Informed Consent, Privacy Notice, Upload or Custom. | 1 | Patients — Docs · Add document · 1 Choose type · Desktop | Open | 1 | 2027-02-03 | 2027-02-03 |  | Not started
M03.09.04 | M03 | Patients | Docs | Prescription | Medicines and dosage on the clinic Rx letterhead. | 1 | Patients — Docs · Add document · 2 Prescription · Desktop | Open | 3 | 2027-02-04 | 2027-02-08 |  | Not started
M03.09.05 | M03 | Patients | Docs | Dental certificate | Certify an exam or procedure for school or work. | 1 | Patients — Docs · Add document · 3 Dental Certificate · Desktop | Open | 2 | 2027-02-09 | 2027-02-10 |  | Not started
M03.09.06 | M03 | Patients | Docs | Informed consent | Record patient consent before a procedure. | 1 | Patients — Docs · Add document · 4 Informed Consent · Desktop | Open | 2 | 2027-02-11 | 2027-02-12 |  | Not started
M03.09.07 | M03 | Patients | Docs | Privacy notice & consent | Data-privacy notice with tap-to-sign and signed states. | 3 | Patients — Docs · Add document · 4b Privacy Notice and Consent · Desktop Patients — Docs · Add document · 4c Privacy Notice and Consent · Signed · Desktop Patients — Docs · Add document · 4d Privacy Notice · Tap to sign · Desktop | Open | 3 | 2027-02-15 | 2027-02-17 |  | Not started
M03.09.08 | M03 | Patients | Docs | Upload document | Attach a scan, x-ray or PDF. | 1 | Patients — Docs · Add document · 5 Upload · Desktop | Open | 2 | 2027-02-18 | 2027-02-19 |  | Not started
M03.09.09 | M03 | Patients | Docs | Custom document | Free-form document on the clinic letterhead. | 1 | Patients — Docs · Add document · 6 Custom · Desktop | Open | 2 | 2027-02-22 | 2027-02-23 |  | Not started
M03.10.01 | M03 | Patients | Images | Photos | Photo grid including the empty state. | 2 | Patients — Details · Images · Photos · Empty · Desktop Patients — Details · Images · Desktop | Open | 2 | 2027-02-24 | 2027-02-26 |  | Not started
M03.10.02 | M03 | Patients | Images | Upload photos | Upload new photos (empty and filled states). | 2 | Patients — Details · Images · Upload photos · Empty · Desktop Patients — Details · Images · Upload photos · Desktop | Open | 2 | 2027-03-01 | 2027-03-02 |  | Not started
M03.10.03 | M03 | Patients | Images | Albums | Group photos into albums. | 1 | Patients — Details · Images · Albums · Desktop | Open | 2 | 2027-03-03 | 2027-03-04 |  | Not started
M03.10.04 | M03 | Patients | Images | Album detail | View an album; add photos from patient photos or upload new. | 3 | Patients — Details · Images · Album detail · Desktop Patients — Details · Images · Album detail · Add photos · Desktop Patients — Details · Images · Album detail · Add photos · Upload new · Desktop | Open | 2 | 2027-03-05 | 2027-03-08 |  | Not started
M03.10.05 | M03 | Patients | Images | Photo viewer | Full-size viewer with edit details and delete confirmation. | 3 | Patients — Details · Images · Photo viewer · Desktop Patients — Details · Images · Photo viewer · Edit details · Desktop Patients — Details · Images · Photo viewer · Delete confirmation · Desktop | Open | 3 | 2027-03-09 | 2027-03-11 |  | Not started
M04.01.01 | M04 | Reports | Patients Report | Filters & dentist selection | Empty state with filters and dentist dropdown. | 1 | Reports — Patients Report · Patient Details · Empty · Dentist dropdown | Open | 2 | 2026-11-18 | 2026-11-19 |  | Not started
M04.01.02 | M04 | Reports | Patients Report | Patient details report | Age, gender, insurance, effective date, status, tag. | 1 | Reports — Patients Report · Patient Details · Results | Open | 2 | 2026-11-20 | 2026-11-23 |  | Not started
M04.01.03 | M04 | Reports | Patients Report | Procedure report | Procedures done per patient by date. | 1 | Reports — Patients Report · Procedure · Results | Open | 2 | 2026-11-24 | 2026-11-25 |  | Not started
M04.01.04 | M04 | Reports | Patients Report | Tooth condition report | Findings per tooth number. | 1 | Reports — Patients Report · Tooth Condition · Results | Open | 2 | 2026-11-26 | 2026-11-27 |  | Not started
M04.01.05 | M04 | Reports | Patients Report | Filter columns | Choose which columns to show and export. | 1 | Reports — Patients Report · Patient Details · Results · Filter columns | Open | 1 | 2026-12-01 | 2026-12-01 |  | Not started
M04.02.01 | M04 | Reports | Commission Report | Commission report | Transactions with total, paid and commission; Pending / Available / Paid out; page totals. | 1 | Reports — Commission Report · Results | Open | 3 | 2026-12-02 | 2026-12-04 |  | Not started
M05.01.01 | M05 | Account | Profile | Profile details | Profile, email, mobile number and password overview. | 1 | Profile — Account · Profile | Open | 1 | 2026-10-30 | 2026-10-30 |  | Not started
M05.01.02 | M05 | Account | Profile | Update profile | Edit name and profile photo. | 1 | Profile — Account · Modal · Update profile | Open | 1 | 2026-11-03 | 2026-11-03 |  | Not started
M05.01.03 | M05 | Account | Profile | Update email | Change email address. | 1 | Profile — Account · Modal · Update email | Open | 1 | 2026-11-04 | 2026-11-04 |  | Not started
M05.01.04 | M05 | Account | Profile | Verify email | Enter the verification code for a new email. | 1 | Profile — Account · Modal · Verify email address | Open | 1 | 2026-11-05 | 2026-11-05 |  | Not started
M05.01.05 | M05 | Account | Profile | Update mobile number | Change mobile number. | 1 | Profile — Account · Modal · Update mobile number | Open | 1 | 2026-11-06 | 2026-11-06 |  | Not started
M05.01.06 | M05 | Account | Profile | Update password | Change password. | 1 | Profile — Account · Modal · Update password | Open | 1 | 2026-11-09 | 2026-11-09 |  | Not started
M05.02.01 | M05 | Account | My Signature | Signature · empty | No signature saved yet. | 1 | Profile — Account · My signature · Empty | Open | 1 | 2026-11-10 | 2026-11-10 |  | Not started
M05.02.02 | M05 | Account | My Signature | Signature · saved | Saved signature preview. | 1 | Profile — Account · My signature · Saved | Open | 1 | 2026-11-11 | 2026-11-11 |  | Not started
M05.02.03 | M05 | Account | My Signature | Draw signature | Draw a signature in a modal. | 1 | Profile — Account · My signature · Draw modal | Open | 2 | 2026-11-12 | 2026-11-13 |  | Not started
M05.02.04 | M05 | Account | My Signature | Upload signature | Upload a signature image. | 1 | Profile — Account · My signature · Upload modal | Open | 1 | 2026-11-16 | 2026-11-16 |  | Not started
M05.02.05 | M05 | Account | My Signature | Remove signature | Confirm removing the signature. | 1 | Profile — Account · My signature · Remove confirmation | Open | 1 | 2026-11-17 | 2026-11-17 |  | Not started
[6 empty] | 89 |  | Total | 166
Formulas:
Planned start = INDEX('Module Timeline'!$E:$E,MATCH([Module ID],'Module Timeline'!$A:$A,0))
Planned start = WORKDAY([Planned end, row above],1,Holidays)
Planned end = WORKDAY([Planned start],MAX([Est. days],1)-1,Holidays)

## Screen List
Screen List
Every Figma frame and the task it belongs to.
# | Task ID | Module | Feature / Task | Figma frame name | Figma
1 | M01.01.01 | Dashboard | Greeting & day summary | Dashboard — Dentist · Overview | Open
2 | M02.01.01 | Appointments | Day view | Appointments - Day | Open
3 | M02.01.01 | Appointments | Day view | Appointments - Day | Open
4 | M02.01.02 | Appointments | Date filter | Appointments - Day · Date filter | Open
5 | M02.01.03 | Appointments | Week view | Appointments - Week | Open
6 | M02.01.04 | Appointments | Month view | Appointments - Month | Open
7 | M02.02.01 | Appointments | View details | Appointments - Day · Details · Modal | Open
8 | M02.02.02 | Appointments | Status states | Details modal · Pending | Open
9 | M02.02.02 | Appointments | Status states | Details modal · Confirmed | Open
10 | M02.02.02 | Appointments | Status states | Details modal · Rescheduled | Open
11 | M02.02.02 | Appointments | Status states | Details modal · Cancelled | Open
12 | M02.02.02 | Appointments | Status states | Details modal · Completed | Open
13 | M02.02.02 | Appointments | Status states | Details modal · Completed | Open
14 | M02.02.03 | Appointments | Reschedule | Details modal · Reschedule | Open
15 | M02.02.04 | Appointments | Cancel appointment | Cancel dialog | Open
16 | M02.02.05 | Appointments | More actions menu | Details modal · Confirmed · More action open | Open
17 | M02.02.06 | Appointments | Change procedure | Details modal · Change procedure · Multi-select | Open
18 | M02.02.07 | Appointments | Last visit history | Details modal · Last visit (expanded) | Open
19 | M02.03.01 | Appointments | Select patient | Appointments - Add appointment · Select patient (1 empty) | Open
20 | M02.03.01 | Appointments | Select patient | Appointments - Add appointment · Select patient (2 dropdown) | Open
21 | M02.03.01 | Appointments | Select patient | Appointments - Add appointment · Select patient (3 selected) | Open
22 | M02.03.02 | Appointments | Select procedure & schedule | Appointments - Add appointment | Open
23 | M02.03.03 | Appointments | All procedures list | Appointments - Add appointment · All procedures | Open
24 | M02.03.04 | Appointments | Review & confirm | Appointments - Add appointment · Review & confirm | Open
25 | M02.03.05 | Appointments | Booking confirmation | Appointments - Add appointment · Booked | Open
26 | M02.04.01 | Appointments | Requests drawer | Appointments — Calendar - Requests drawer | Open
27 | M02.04.02 | Appointments | Request details | Appointments — Calendar - Requests drawer · View details | Open
28 | M03.01.01 | Patients | Patient list | Patients — List | Open
29 | M03.02.01 | Patients | Add patient form | Patients — Add patient · Modal · v2 (field list) · Desktop | Open
30 | M03.02.02 | Patients | Add success | Patients — Add patient · Success · Desktop | Open
31 | M03.02.03 | Patients | Duplicate detection | Patients — Add patient · Duplicate found · v1 (comparison) · Desktop | Open
32 | M03.02.04 | Patients | Merge records | Patients — Add patient · Merge confirmation · Desktop | Open
33 | M03.02.05 | Patients | Merge success | Patients — Add patient · Merge success · Desktop | Open
34 | M03.04.01 | Patients | View general info | Patients — Details · General 1 · Desktop | Open
35 | M03.04.02 | Patients | Edit general info | Patients — Details · General 1 · Edit · Desktop | Open
36 | M03.05.01 | Patients | View medical history | Patients — Details · Medical History · Layout C · Desktop | Open
37 | M03.05.02 | Patients | Edit medical history | Patients — Details · Medical History · Layout C · Edit · Desktop | Open
38 | M03.06.01 | Patients | Chart · collapsed | Patients — Details · Dental Record Chart · Many findings · Collapsed · Desktop | Open
39 | M03.06.02 | Patients | Chart · expanded | Patients — Details · Dental Record Chart · Many findings · Expanded · Desktop | Open
40 | M03.06.03 | Patients | Full-screen chart | Patients — Dental Record Chart · Full screen · Desktop | Open
41 | M03.07.01 | Patients | Transaction list | Patients — Details · Transaction Record · Desktop | Open
42 | M03.07.02 | Patients | Add transaction · type | Patients — Details · Transaction Record · Add transaction · Transaction type · Layout B · Desktop | Open
43 | M03.07.03 | Patients | Procedure transaction | Patients — Details · Transaction Record · Add transaction · Procedure · Layout B · Desktop | Open
44 | M03.07.03 | Patients | Procedure transaction | Patients — Details · Transaction Record · Add transaction · Procedure · Layout B · Typing a procedure · Desktop | Open
45 | M03.07.04 | Patients | Add procedure | Patients — Details · Transaction Record · Add transaction · Procedure · Add procedure · Desktop | Open
46 | M03.07.05 | Patients | Browse all procedures | Patients — Details · Transaction Record · Add transaction · Procedure · Add procedure · All procedures · Desktop | Open
47 | M03.07.06 | Patients | Purchase item transaction | Patients — Details · Transaction Record · Add transaction · Purchase Item · Desktop | Open
48 | M03.07.07 | Patients | Add item | Patients — Details · Transaction Record · Add transaction · Purchase Item · Add item · Desktop | Open
49 | M03.07.08 | Patients | Browse all items | Patients — Details · Transaction Record · Add transaction · Purchase Item · Add item · All items · Desktop | Open
50 | M03.08.01 | Patients | Statement of account | Patients — Details · Statement of Account · Layout B · Desktop | Open
51 | M03.09.01 | Patients | Document list | Patients — Details · Docs · Layout C · Desktop | Open
52 | M03.09.02 | Patients | Row actions menu | Patients — Details · Docs · Layout C · Row menu · Desktop | Open
53 | M03.09.03 | Patients | Add document · choose type | Patients — Docs · Add document · 1 Choose type · Desktop | Open
54 | M03.09.04 | Patients | Prescription | Patients — Docs · Add document · 2 Prescription · Desktop | Open
55 | M03.09.05 | Patients | Dental certificate | Patients — Docs · Add document · 3 Dental Certificate · Desktop | Open
56 | M03.09.06 | Patients | Informed consent | Patients — Docs · Add document · 4 Informed Consent · Desktop | Open
57 | M03.09.07 | Patients | Privacy notice & consent | Patients — Docs · Add document · 4b Privacy Notice and Consent · Desktop | Open
58 | M03.09.07 | Patients | Privacy notice & consent | Patients — Docs · Add document · 4c Privacy Notice and Consent · Signed · Desktop | Open
59 | M03.09.07 | Patients | Privacy notice & consent | Patients — Docs · Add document · 4d Privacy Notice · Tap to sign · Desktop | Open
60 | M03.09.08 | Patients | Upload document | Patients — Docs · Add document · 5 Upload · Desktop | Open
61 | M03.09.09 | Patients | Custom document | Patients — Docs · Add document · 6 Custom · Desktop | Open
62 | M03.10.01 | Patients | Photos | Patients — Details · Images · Photos · Empty · Desktop | Open
63 | M03.10.01 | Patients | Photos | Patients — Details · Images · Desktop | Open
64 | M03.10.02 | Patients | Upload photos | Patients — Details · Images · Upload photos · Empty · Desktop | Open
65 | M03.10.02 | Patients | Upload photos | Patients — Details · Images · Upload photos · Desktop | Open
66 | M03.10.03 | Patients | Albums | Patients — Details · Images · Albums · Desktop | Open
67 | M03.10.04 | Patients | Album detail | Patients — Details · Images · Album detail · Desktop | Open
68 | M03.10.04 | Patients | Album detail | Patients — Details · Images · Album detail · Add photos · Desktop | Open
69 | M03.10.04 | Patients | Album detail | Patients — Details · Images · Album detail · Add photos · Upload new · Desktop | Open
70 | M03.10.05 | Patients | Photo viewer | Patients — Details · Images · Photo viewer · Desktop | Open
71 | M03.10.05 | Patients | Photo viewer | Patients — Details · Images · Photo viewer · Edit details · Desktop | Open
72 | M03.10.05 | Patients | Photo viewer | Patients — Details · Images · Photo viewer · Delete confirmation · Desktop | Open
73 | M04.01.01 | Reports | Filters & dentist selection | Reports — Patients Report · Patient Details · Empty · Dentist dropdown | Open
74 | M04.01.02 | Reports | Patient details report | Reports — Patients Report · Patient Details · Results | Open
75 | M04.01.03 | Reports | Procedure report | Reports — Patients Report · Procedure · Results | Open
76 | M04.01.04 | Reports | Tooth condition report | Reports — Patients Report · Tooth Condition · Results | Open
77 | M04.01.05 | Reports | Filter columns | Reports — Patients Report · Patient Details · Results · Filter columns | Open
78 | M04.02.01 | Reports | Commission report | Reports — Commission Report · Results | Open
79 | M05.01.01 | Account | Profile details | Profile — Account · Profile | Open
80 | M05.01.02 | Account | Update profile | Profile — Account · Modal · Update profile | Open
81 | M05.01.03 | Account | Update email | Profile — Account · Modal · Update email | Open
82 | M05.01.04 | Account | Verify email | Profile — Account · Modal · Verify email address | Open
83 | M05.01.05 | Account | Update mobile number | Profile — Account · Modal · Update mobile number | Open
84 | M05.01.06 | Account | Update password | Profile — Account · Modal · Update password | Open
85 | M05.02.01 | Account | Signature · empty | Profile — Account · My signature · Empty | Open
86 | M05.02.02 | Account | Signature · saved | Profile — Account · My signature · Saved | Open
87 | M05.02.03 | Account | Draw signature | Profile — Account · My signature · Draw modal | Open
88 | M05.02.04 | Account | Upload signature | Profile — Account · My signature · Upload modal | Open
89 | M05.02.05 | Account | Remove signature | Profile — Account · My signature · Remove confirmation | Open

## Setup
Project Setup
Edit the blue cells. All dates in the plan recalculate from these.
Project start date | 2026-10-19 | Monday, Oct 19, 2026 is a placeholder. Set it to the real kickoff date.
Legend
Blue text |  | Input you can change (start date, est. days, holidays). Typing a date over a Start formula pins that task.
Yellow fill |  | For the dev team to fill in (assignee, status, actual dates, remarks).
Black text |  | Formula. Don't type over it unless you mean to override it.
Scheduling rules
1. | Dates skip weekends and the holidays below (WORKDAY).
2. | Inside a module, tasks run one after another: each starts the working day after the previous one ends.
3. | Modules run on 3 parallel tracks after Global / Shell: A = Appointments → Dashboard, B = Patients, C = Account → Reports.
4. | Est. days are placeholder estimates for one developer, based on screen count and complexity. The dev team should replace them.
Holidays (non-working days) |  | Source: Philippine regular and special non-working days; verify against the official proclamation for 2026 and 2027.
Date | Holiday
2026-11-02 | All Souls' Day (special non-working, verify)
2026-11-30 | Bonifacio Day
2026-12-08 | Feast of the Immaculate Conception
2026-12-24 | Christmas Eve
2026-12-25 | Christmas Day
2026-12-30 | Rizal Day
2026-12-31 | Last Day of the Year
2027-01-01 | New Year's Day
2027-02-25 | EDSA Revolution Anniversary (verify)
2027-03-25 | Maundy Thursday
2027-03-26 | Good Friday
2027-04-09 | Araw ng Kagitingan
Note on B4: Assumption: Monday after the module list was finalised (Oct 11, 2026). Change to the real kickoff date.